## Sheet1
Status | Phase | Subphase | Task | Item | Description
- | 0 | 1 | 0 | 0 | Planning Products
1 | 0 | 1 | 0 | 1 | Create This Product Plan
- | 0 | 1 | 0 | 2 | Statement of Objectives
- | 0 | 1 | 0 | 3 | Network Architecture Design
- | 0 | 1 | 0 | 4 | Network Component Software List
- | 1 | 1 | 0 | 0 | Network Build
- | 1 | 1 | 1 | 1 | Build Documentation
- | 1 | 1 | 1 | 1 | GitHub Repository
- | 1 | 2 | 1 | 0 | Vagrant Build Scripts - Routers
- | 1 | 2 | 1 | 1 | External
- | 1 | 2 | 1 | 2 | DMZ
- | 1 | 2 | 1 | 3 | Internal
- | 1 | 2 | 1 | 4 | Development
- | 1 | 2 | 2 | 0 | Vagrant Build Scripts - DMZ Servers
- | 1 | 2 | 2 | 1 | Web
- | 1 | 2 | 2 | 2 | Database
- | 1 | 2 | 2 | 3 | DNS
- | 1 | 2 | 2 | 4 | VPN
- | 1 | 2 | 2 | 5 | Email
- | 1 | 2 | 3 | 0 | Vagrant Build Scripts - Enterprise Servers
- | 1 | 2 | 3 | 1 | Authentication
- | 1 | 2 | 3 | 2 | Email
- | 1 | 2 | 3 | 3 | File Service
- | 1 | 2 | 4 | 0 | Vagrant Build Scripts - Enterprise Workstations
- | 1 | 2 | 4 | 1 | SMB Client
- | 1 | 2 | 5 | 0 | Vagrant Build Scripts - Development Servers
- | 1 | 2 | 5 | 1 | Version Control
- | 1 | 2 | 5 | 2 | Trouble Ticketing
- | 1 | 2 | 6 | 0 | Vagrant Build Scripts - Development Workstations
- | 1 | 2 | 6 | 1 | Unix Workstations
- | 1 | 2 | 7 | 0 | Vagrant Build Scripts - Network Servers
- | 1 | 2 | 7 | 1 | Firewall
- | 1 | 2 | 7 | 2 | Web Proxy
- | 1 | 2 | 7 | 3 | NAT
- | 1 | 2 | 7 | 4 | Logging Aggregator
- | 1 | 2 | 7 | 5 | Email Filter
- | 1 | 2 | 7 | 6 | DoS Filter
- | 1 | 2 | 7 | 7 | IP Integrity
- | 1 | 2 | 7 | 8 | IPS
- | 1 | 2 | 7 | 9 | Vuln Mgmt
- | 1 | 2 | 7 | 10 | Patch Mgmt
- | 1 | 2 | 7 | 11 | Asset Mgmt
- | 1 | 2 | 7 | 12 | SOC Workstation
- | 1 | 2 | 7 | 13 | Malware Flow Analyzer
- | 1 | 3 | 1 | 0 | Vmware Port
- | 1 | 4 | 1 | 0 | Test Cases:
- | 1 | 4 | 1 | 1 | Running status of all components
- | 1 | 4 | 1 | 2 | Network status of all components
- | 1 | 4 | 1 | 3 | Service status (simple) of all component services
- | 2 | 1 | 1 | 0 | Capability Development